Project Title: PLC Migration and HMI Upgrade for Aseptic Holding Vessel

Student Name: Nathan Harris		Employer’s Name: Premier Foods

Introduction

This project proposal will serve to outline the various stages and requirements of the project to be carried out including research, design, implementation and commissioning. This project is within the scope of an Aseptic Holding Vessel control system, which is part of a larger Infusion Process Plant. It will consist of the migration of a Siemens S7-300 PLC to a Siemens S7-1500F safety PLC. Alongside this, the replacement of a Simatic ProTool HMI will be upgraded to a newer HMI which will host an Inductive Automation – Ignition Edge platform and display an Ignition Perspective client session. The main reason for this upgrade is part of a smart factory initiative to increase cybersecurity, diagnostic capability and the availability of logical safety for future integration with other processes. Additionally, there have been historical card failures on the PLC rack, for which replacements are becoming expensive as S7-300 parts are being phased out. Lastly the current HMI is inoperative and obsolete, so a new solution is required to replace it.

Aim

The project aim is to modernise the PLC as part of an initiative to create a cybersecure OT network, advance the safety of the process in the future, and to create an easy-to-use HMI with clear information and control elements for end users that will conform to accessibility and EDI standards.

Objectives

Research Objectives

- To review technical documents such as component specifications, migration/installation guides, firmware/software release notes, HMI design standards, design guides and cybersecurity documents by 27th October 2025

- To review the most up-to-date policies and standards such as latest cyber security policies/standards and recommendations within an OT network and research on accessibility for the PLC/HMI design to ensure it complies with EDI requirements by 27th October 2025

- To gather and document data from the existing system to include the current PLC configuration and program, the current HMI configuration and screen layout, and information on the current system architecture to include I/O components and network configuration by 3rd November 2025

Design Objectives

- To redesign the HMI screens to be more in-line with EDI requirements and to create better control and visualisation for the end user by 17th November 2025

- Create a plan for implementing, I/O checks and commissioning by 17th November 2025

- To migrate the program and adapt as necessary to newer functions and where possible make it structured clearly for any engineers who may need to fault find by 8th December 2025

Implementation Objectives

- To order any parts and materials required for the project by 05th Jan 2026

- To create the HMI program with relevant screens according to design by 9th March 2026

- To replace the CPU in the panel along with any upgraded I/O by 23rd March 2026

- To replace the HMI in the panel door by 23rd March 2026

Commissioning Objectives

- To complete and I/O checks and carry out various tests to ensure it is all performing correctly, including any network communications, according to the commissioning plan by 6th April 2026

Report Objectives

- To complete the project progress report and hand in with any supporting documentation by 16th January 2026.

- To complete the project report and hand in with any supporting documentation by 17th April 2026.

- To complete the project presentation on the specified date (TBC – between 20th & 29th April 2026)

Key Details

The industry supervisor for this project will be Dave Stephens: (dave.stephens@premierfoods.co.uk)

The work carried out will be at the Ambrosia Creamery in Lifton, Devon. Any research and design tasks will be carried out in the main office block. Implementation and commissioning will need to be lineside in the APV process area. A risk assessment has been carried out for the proposed plan. The EDI test and Ethical Approval application has been carried out as required by the university. The time plan for the project can be viewed on the next page.